## Sheet1
Group Name: | Vista Enthusiasts
Task ID | Task Name | Responsible: | Task Dependency: | Start Date | End Date | Duration(Days): | Days Remaining
1 | I2 Analysis | All |  | 2020-01-23 | 2020-01-30 | 7 | 0
2 | Update Iteration1 to Iteration 2 | All | 1 | 2020-01-31 | 2019-02-06 | 6 | 0
3 | System Requirements | Meelan | 1 | 2020-02-11 | 2020-02-18 | 7 | 0
4 | Use Cases | Nathan | 1 | 2020-02-11 | 2020-02-18 | 7 | 0
5 | Architecture Consideration | Scott | 1 | 2020-02-11 | 2020-02-18 | 7 | 0
6 | Risk Analysis | Joseph | 1 | 2020-02-11 | 2020-02-18 | 7 | 0
7 | Gantt Chart | Mohammed | 1 | 2020-02-13 | 2020-02-18 | 1 | 0
8 | Prototypes | Scott | 1 | 2020-02-11 | 2020-02-18 | 7 | 0
9 | Presentation | All | I2 Document Complete | 2020-02-18 | 2020-02-19 | 2 | 0
10 | Design Presneation | All |  | 2020-02-18 | 2020-02-19 | 2 | 0
11 | Practice Presentation/Final Check | All | Presnetation Complete | 2020-02-18 | 2020-02-19 | 2 | 0

## Sheet2
January/February
23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20